## Assumptions
Prior Authorization Modernization — Cost Model
Assumptions
Prepared for Richard Williams, IBM • July 2026
All figures below are illustrative planning-level placeholders (not quotes) — cells in blue are inputs. Replace with actual rates/quotes when known.
Labor Rates ($ / day, blended)
Role | Daily Rate ($) |  | Note
Tech Lead | 1450 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Backend/FHIR Engineer 1 | 1100 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Backend/FHIR Engineer 2 | 1100 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Data/Integration Engineer | 1100 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Frontend Engineer | 1000 |  | Illustrative U.S. blended consulting rate — replace with actual rate
QA Engineer | 900 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Security Engineer | 1250 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Product/Clinical SME | 1300 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Project Manager | 1050 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Clinical Policy Reviewer | 950 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Schedule Assumptions
Working days per week | 5 |  | Standard 5-day work week
Build duration (weeks) | 18 |  | From the Implementation Plan — total project End Week
Avg. working days per month | 21.7 |  | 52 weeks x 5 days / 12 months
Build duration (months) | 4.1475 |  | Calculated from build duration in weeks
Cloud Hosting — Infrastructure (Monthly, USD)
Cloud Provider | Azure |  | Select AWS or Azure — drives the Total Infrastructure cost below. Default set to Azure per the Idaho Medicaid CMS-0057 assessment (Infrastructure Q1: Azure preferred for state projects)
Component | AWS ($/mo) | Azure ($/mo) | Note
Compute — CRD/DTR/PAS microservices | 1400 | 1500 | AWS Fargate (ECS) / Azure Container Apps
Managed FHIR Datastore | 2800 | 3200 | AWS HealthLake / Azure Health Data Services (FHIR service)
PA Aggregation DB & Object Storage | 600 | 650 | RDS Postgres + S3 / Azure Cosmos DB + Blob Storage
DTR SMART App Hosting (CDN) | 300 | 300 | CloudFront + S3 / Azure Static Web Apps + CDN
API Gateway / Load Balancer | 250 | 280 | AWS ALB + API Gateway / Azure API Management
Backup & Disaster Recovery | 400 | 450 | Cross-region backup and point-in-time recovery
Monitoring & Logging | 300 | 320 | Amazon CloudWatch / Azure Monitor
Security — WAF, Key Mgmt, Secrets | 250 | 270 | AWS WAF + KMS / Azure Front Door WAF + Key Vault
Total Infrastructure (Monthly, Selected Provider) | 6970
Integration Scope — EMR Connections
EMR connections included in base build | 1 |  | Base build (Phase 4b) integrates one EMR via generic US Core v3
Total EMR connections in scope | 4 |  | Idaho: Epic + Oracle Health/Cerner + MEDITECH + 1 platform for remaining independent/CAH facilities — see Idaho EMR & Facility Landscape below
Cost per additional EMR connection (one-time) | 35000 |  | Vendor app-store certification (e.g., Epic App Orchard), sandbox integration & testing
Cost per additional EMR connection (monthly, ongoing) | 500 |  | Ongoing vendor fees + maintenance per connected EMR
Additional EMR connections | 3 |  | Total minus what the base build already includes
Idaho EMR & Facility Landscape
Research-based facility counts per EMR platform, current as of July 2026 (see chat for sources). The ‘Platform’ rows above cover the one-time engineering cost to integrate with each EMR VENDOR once; every individual hospital/facility running that vendor still needs its own site rollout — that per-facility cost is priced separately below.
EMR Platform | Idaho Hospital Facilities |  | Note / Source
Epic | 7 |  | St. Luke's Health System (6 hospitals) + Kootenai Health (1) — both confirmed Epic
Oracle Health / Cerner | 2 |  | Saint Alphonsus Idaho facilities (Boise + Nampa); Trinity Health parent may migrate to Epic over time — monitor
MEDITECH | 9 |  | HCA/Eastern Idaho Regional Medical Center (1, confirmed Expanse) + ~8 estimated critical access hospitals (MEDITECH targets 1-200 bed facilities)
Other / Unconfirmed (CPSI, Cerner CommunityWorks, athenahealth, independent) | 37 |  | Remaining Idaho hospitals, mostly small critical access facilities — vendor mix not individually confirmed, needs direct payer/facility outreach
Total Idaho Hospital Facilities | 55 |  | Idaho: 55 hospitals total, incl. 27 CMS-designated critical access hospitals (Becker's Hospital Review / RHT Compass, 2025)
Facilities in scope for initial deployment | 18 |  | Default = the 3 confirmed platforms only (Epic 7 + Oracle Health/Cerner 2 + MEDITECH 9); expand once the 'Other/Unconfirmed' 37 are vendor-confirmed
Cost per facility install (one-time) | 4000 |  | Site-specific go-live: order-set/workflow validation, local IT coordination, provider orientation — much lighter than the platform-level build
Cost per facility install (monthly, ongoing) | 150 |  | Per-site monitoring, credential rotation, minor local config support
Total Facility Rollout Cost (one-time) | 72000
Total Facility Connectivity Cost (monthly, ongoing) | 2700
Idaho Medicaid -- CMS-0057 Assessment Findings (Reference)
Source: CMS-0057 Assessment Questionnaire completed by Idaho Medicaid, dated 7/27/2026. These are real, payer-reported figures used to ground and sanity-check the assumptions above -- most cells below are reference-only (not formula inputs) unless noted.
Finding | Value / Answer |  | Cost model implication
Total covered lives (all plans) | 307,929 (FFS/Medicaid); 305,346 Dental/NEMT/BH; 26,546 Duals |  | Cross-check only -- not directly used in labor/infra formulas
In-network providers | 32,000 |  | Includes all provider/facility NPIs, not just physicians -- do not conflate with EMR platform or facility-install counts above
Medical PAs per month / Drug (pharmacy) PAs per month | 3,300 / 3,910 (~86,760/year combined) |  | No PA-volume-driven cost exists yet in this model (EDI/watsonx lines are flat monthly estimates) -- flagged as a refinement opportunity
Top EMR(s) used by network providers | Only Epic confirmed; 2nd and 3rd EMR left blank on the assessment |  | Payer itself lacks full network EMR visibility -- see new 'Provider EMR & Network Discovery' one-time cost above
Total number of medical guidelines/policies | Left blank -- unknown even internally |  | Confirms the Policy Ingestion 'Policies per payer' assumption is a true placeholder industry-wide, not just a gap in this model -- see new 'Payer Policy Count Discovery' cost above
Medical guideline vendor | MCG (not InterQual, not both) |  | Third-Party Licensing above updated: InterQual defaulted to $0
Guidelines already codified/computable? | Not answered (blank) |  | If MCG content is already API-accessible/computable, Policy Ingestion review cost could be materially lower than modeled -- confirm with payer/vendor before finalizing
PA required by service line | NOT required for: Radiology, High-Tech Radiology, Radiation Therapy, MSK, Sleep Studies, Chiropractic, Post-Acute Care. Required for: Inpatient Admissions, Transplants, Cardiology, Behavioral Health, PT/OT/ST, DME, Diabetic Supplies, Home Health, Air Ambulance |  | Imaging/radiology -- the flagship use case in this solution's design -- is PA-EXEMPT for Idaho Medicaid; re-scope DTR rule priorities toward inpatient/transplant/cardiology/behavioral-health/DME instead
Current PA exchange channel (all 18 service lines) | 100% X12 278/275 + File-Based + Web Portal -- zero FHIR API or non-FHIR API in use anywhere |  | EDI Translator (X12 278/275) is the critical near-term path, not a secondary fallback -- Claim/$submit (FHIR) has no live counterpart yet at this payer
Distinct UM vendors administering PA | Telligen (most medical), Magellan (behavioral health), Prime (pharmacy/diabetic supplies), Internal (home health, air ambulance, DD waiver) |  | Drove the new 'Additional UM sub-vendors per payer' cost above
Actual average PA turnaround time (TAT) | 289 hours 14 min (~12 days) for pharmacy, mostly fax-based; contractual target is 7 days (168 hrs) standard / 72 hrs urgent; medical TAT not quantified ('dependent on business units') |  | Current process already misses today's own contractual SLA -- strengthens the automation ROI case; not a direct cost input
Auto-approval today | Yes for pharmacy; No for medical |  | Medical PA (this solution's focus) starts from a zero-automation baseline
CMS-0057 Prior Authorization API maturity (self-rated 1-5) | 2 -- Initial: planned but not yet implemented |  | Confirms the dual-mode CRD client/fallback recommendation in the architecture plan; payer has no live PA API today
Cloud platform preference | Azure for state projects (vendor-dependent otherwise) |  | Cloud Provider default above changed from AWS to Azure
Security protocols supported (OAuth2, SAML, UDAP, SMART on FHIR, mTLS) | All left blank/unanswered on the assessment |  | No confirmed security/auth posture yet -- treat OAuth2/SMART launch design as needing direct payer discovery, not an assumption
Existing EMR integration | 'No -- we do not currently integrate with EMRs' |  | Confirms all EMR connection work in this model is greenfield, not incremental
Integration Scope — Payer Connections
A single 'payer' relationship is rarely one integration point -- the Idaho Medicaid CMS-0057 assessment shows PA is administered through 4+ independent UM vendors by service line (Telligen for most medical, Magellan for behavioral health, Prime for pharmacy/diabetic supplies, Internal for home health/air ambulance), all via X12/File/Portal today, none via FHIR API. Sub-vendor integrations are priced separately below.
Production payer connections in scope | 3 |  | Each payer requires its own CRD/DTR/PAS endpoint onboarding & trading partner agreement
Cost per payer onboarding (one-time) | 20000 |  | Endpoint conformance testing, EDI 278/275 mapping validation, trading partner agreement, go-live certification
Cost per payer connection (monthly, ongoing) | 750 |  | Monitoring + per-payer clearinghouse/EDI fees
Additional UM sub-vendors per payer (avg) | 3 |  | Idaho Medicaid: Magellan (behavioral health) + Prime (pharmacy/diabetic supplies) + Internal (home health/air ambulance), beyond the primary UM vendor already priced above
Cost per UM sub-vendor integration (one-time) | 8000 |  | Lighter than a full payer onboarding -- reuses the parent payer's trading partner agreement
Cost per UM sub-vendor integration (monthly, ongoing) | 300 |  | Monitoring + sub-vendor-specific EDI/file-feed maintenance
Other Endpoints
EDI clearinghouse connection setup (one-time) | 8000 |  | One-time trading-partner setup, distinct from the monthly translator fee below
Additional HIE / data-source connections | 0 |  | State HIE or other external clinical data source — optional, defaults to none
Cost per additional HIE connection (one-time) | 15000 |  | Only applies if the count above is > 0
Third-Party Licensing
Item | Cost |  | Note
Milliman Care Guidelines API (annual) | 60000 |  | Idaho Medicaid CMS-0057 assessment (Q23) confirms MCG as the sole guideline vendor -- this line represents that MCG license; confirm exact fee with vendor
InterQual API (annual) | 0 |  | Set to $0 by default -- Idaho Medicaid assessment shows MCG only, not InterQual; re-enable only if a specific payer confirms InterQual use
EDI Clearinghouse / Translator (monthly) | 1500 |  | Transaction-based estimate for X12 278/275
watsonx / GenAI Usage — Build Phase (monthly) | 2000 |  | Lower volume during build/test
watsonx / GenAI Usage — Post-Launch (monthly) | 4000 |  | Estimated production volume
Infor Cloverleaf — Optional COTS Integration Engine
Infor Cloverleaf is a healthcare-focused HL7/FHIR/Da Vinci-capable integration engine that could serve as (or supplement) the custom-built EDI Translator line above. Infor does not publish list pricing -- market benchmarks show roughly $15K-$30K per interface per year in license fees, plus $100K-$400K in professional services for a mid-market deployment (source: public pricing aggregators, not an Infor quote). Figures below reflect Richard's estimate ($100K/year license, $200K one-time install/setup), which falls squarely in that benchmark range.
Include Infor Cloverleaf? | Yes |  | Toggle to No to exclude from all totals -- e.g., if the custom-built EDI Translator is used instead of a COTS engine
Infor Cloverleaf annual license | 100000 |  | Estimate (Richard) -- Infor quotes custom; market range roughly $55K-$120K+/year depending on interface count
Infor Cloverleaf implementation & setup (one-time) | 200000 |  | Estimate (Richard) -- mid-market professional services for interface engines typically run $100K-$400K
CMS-0057-F APIs — Patient Access, Provider Access, Payer-to-Payer
CMS-0057-F requires four FHIR APIs by 1/1/2027: Prior Authorization (the core scope of this entire build, above), Patient Access, Provider Access, and Payer-to-Payer. This section prices the three that are additive to the Prior Auth build. If Infor Cloverleaf is included above, these three API interfaces are assumed to be built and hosted on that platform rather than as custom FHIR server code -- the labor figures below are lighter than a from-scratch build would require as a result; set Cloverleaf to No and increase these figures if building custom.
Patient Access API (Enhancement)
Idaho Medicaid already operates a Patient Access API via Onyx (CMS-9115-F, confirmed in the CMS-0057 assessment) -- this is an enhancement to add prior-auth status/decision data and upgrade to SMART App Launch 2.0, not a from-scratch build.
Patient Access API enhancement (one-time) | 45000 |  | Add prior-auth data classes + SMART App Launch 2.0 upgrade to existing Onyx-hosted API
Patient Access API — incremental vendor fee (monthly, ongoing) | 500 |  | Incremental fee on top of existing Onyx contract
Provider Access API (Net New Build)
No equivalent exists today. Requires FHIR Bulk Data Access IG v1.0.0, USCDI data classes, backend-services (SMART Backend Services) authentication, and patient-provider attribution logic to determine which providers can pull which patients' data.
Provider Access API build (one-time) | 180000 |  | FHIR endpoint + Bulk Data Access IG + attribution logic + backend-services auth
Provider Access API hosting & maintenance (monthly, ongoing) | 2500 |  | Production hosting, monitoring, attribution data refresh
Payer-to-Payer API (Net New Build + Consent Process)
No equivalent exists today. Requires the FHIR API itself (profiled per Da Vinci PDex), a patient opt-in/consent workflow at enrollment and plan-switch, and CMS-mandated patient educational materials about the data-sharing option.
Payer-to-Payer API build (one-time) | 130000 |  | FHIR endpoint profiled per Da Vinci PDex Implementation Guide
Patient opt-in / consent management workflow (one-time) | 55000 |  | Enrollment + plan-switch consent capture, storage, and revocation UI
Patient educational materials (one-time) | 10000 |  | CMS-mandated member communications about the data-sharing option
Payer-to-Payer API & consent operations (monthly, ongoing) | 2000 |  | Hosting + ongoing consent tracking/revocation processing
Prior Payer Trading Partner Connections (Payer-to-Payer, Supply Side)
This is the other direction of Payer-to-Payer: actually connecting to the prior/concurrent payers a member is requesting data FROM. PLACEHOLDER -- modeled as direct bilateral connections to the largest Idaho-market MA/commercial carriers (e.g., Blue Cross of Idaho, Regence, Molina/SelectHealth, UnitedHealthcare, Humana); Idaho had 48 active Medicare Advantage plans in 2026 across a smaller number of parent organizations. In practice many payers exchange via a shared national payer-to-payer network/hub rather than pure bilateral builds -- confirm hub participation strategy (e.g., a CAQH-style utility) before finalizing this count, as it could substantially reduce the per-connection cost below.
Prior payer trading partners in scope | 8 |  | PLACEHOLDER -- major Idaho-market MA/commercial payers; confirm actual count once hub-vs-bilateral strategy is set
Cost per prior payer connection (one-time) | 12000 |  | Trading partner agreement, FHIR consumer client build/test against that payer's Payer-to-Payer API
Cost per prior payer connection (monthly, ongoing) | 400 |  | Monitoring + credential rotation
Total Prior Payer Connections (one-time) | 96000
Total Prior Payer Connections (monthly, ongoing) | 3200
Total CMS-0057-F APIs (one-time) | 516000
Total CMS-0057-F APIs (monthly, ongoing) | 8200
HIPAA & Compliance Certification
HIPAA Risk Assessment & Gap Remediation (one-time) | 30000 |  | Third-party HIPAA Security Rule risk assessment ahead of go-live
BAA Legal Review & Execution (one-time) | 5000 |  | Legal review/execution of Business Associate Agreements with EMR/payer partners
SOC 2 Type II Readiness + Audit — Year 1 (one-time) | 45000 |  | Common trust requirement for payer/EMR trading partners
SOC 2 Type II Annual Renewal (ongoing/year) | 25000 |  | Recurring annual audit after Year 1
Include HITRUST CSF Certification? | No |  | Optional upgrade — only if required by a specific payer/EMR trading partner
HITRUST CSF Certification (one-time) | 120000 |  | Only applied to totals if 'Include HITRUST' above is Yes
HITRUST CSF Annual Renewal (ongoing/year) | 40000 |  | Only applied to totals if 'Include HITRUST' above is Yes
One-Time Costs (Other)
External Security Penetration Test | 25000 |  | One-time, ahead of go-live
UAT Logistics & Clinical SME Stipends | 8000 |  | One-time, hardening sprint
Provider EMR & Network Discovery | 20000 |  | Idaho Medicaid's own CMS-0057 assessment left 2 of 3 top-EMR fields blank -- the payer itself does not have full visibility into its network's EMR mix; budget a direct survey/outreach effort
Payer Policy Count Discovery & Inventory | 15000 |  | Idaho Medicaid's assessment left 'Total number of medical guidelines' (Q20) blank -- confirm the real policy count/library per payer before finalizing the Policy Ingestion budget below
Total One-Time Costs (Other) | 68000
Contingency % | 15% |  | Applied to Labor + Infrastructure + Licensing + Integration + Compliance + One-Time subtotal
Post Go-Live Support (Ongoing, Monthly)
Backend/FHIR Support Engineer allocation (FTE) | 0.5 |  | Ongoing production support
QA Support allocation (FTE) | 0.25 |  | Ongoing regression/monitoring support
Infra scale-up factor, post-launch | 1.2 |  | Applied to build-phase infra monthly total for production load
Policy Ingestion & Clinical Review (Intelligent Policy Engine -> DTR Rules)
Every payer medical policy the Intelligent Policy Engine converts into a DTR Questionnaire+CQL rule set must be clinically reviewed and signed off before use — this section is unscoped in the base 57-task build plan (S0-03 only validates the pipeline on one sample policy) and needs its own headcount and per-document cost.
Policies per payer — initial ingestion scope | 150 |  | PLACEHOLDER — actual policy library size is unknown; confirm the real count with each payer and update this cell
Total policies — initial ingestion | 450 |  | Production payer connections (above) x policies per payer
New / revised policies per payer, per year | 30 |  | Illustrative — payers typically revise ~15-25% of active policies annually plus add new ones
Total policies processed — annual (ongoing) | 90 |  | Production payer connections (above) x new/revised policies per payer per year
Clinical Policy Reviewer hours per working day | 8 |  | Standard full workday
Review hours per document — initial ingestion | 2 |  | Read source policy, verify AI-extracted JSON/Questionnaire/CQL mapping, validate ICD-10/CPT code sets, sign off
Review hours per document — annual revision | 1 |  | Lighter delta-review against an already-approved baseline
Clinical Policy Reviewer hourly rate | 118.75 |  | Clinical Policy Reviewer daily rate (Labor Rates above) / hours per day
Cost per document — initial ingestion | 237.5 |  | Reviewer hourly rate x initial review hours per document
Cost per document — annual revision | 118.75 |  | Reviewer hourly rate x revision review hours per document
Total Initial Policy Review Cost (one-time) | 106875
Total Annual Policy Revision Review Cost (ongoing) | 10687.5
Implied reviewer FTEs to clear initial backlog within build window | 1.25 |  | Total initial review hours / (build weeks x days/week x hours/day) — staffing guide only

## Task Cost Detail
ID | Phase | Task | Owner Role | Person-Days | Daily Rate ($) | Task Cost ($)
S0-01 | S0 | Repo & Environment Review | Tech Lead | 3 | 1450 | 4350
S0-02 | S0 | Cut feature/phase4-crd-dtr-pas-integration Branch | Tech Lead | 0.5 | 1450 | 725
S0-03 | S0 | Intelligent Policy Engine Schema Spike | Data/Integration Engineer | 5 | 1100 | 5500
S0-04 | S0 | Milliman/InterQual API Access & Licensing Confirmation | Product/Clinical SME | 3 | 1300 | 3900
S0-05 | S0 | Payer Endpoint Directory & Capability Schema | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
S0-06 | S0 | CI/CD & Environment Setup | Tech Lead | 2 | 1450 | 2900
S0-07 | S0 | Confidence-Threshold Policy Workshop | Product/Clinical SME | 2 | 1300 | 2600
4A-01 | 4A | CDS Hooks Client | Backend/FHIR Engineer 1 | 5 | 1100 | 5500
4A-02 | 4A | Prior Auth Service Orchestrator (Skeleton) | Backend/FHIR Engineer 1 | 5 | 1100 | 5500
4A-03 | 4A | Eligibility & Enrollment Check | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4A-04 | 4A | Provider Network Status Check | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4A-05 | 4A | Milliman/InterQual Guideline Check | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4A-06 | 4A | PA-Required Policy Lookup | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
4A-07 | 4A | CDS Card / Coverage Information Builder | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
4A-08 | 4A | CRD Checklist UI Screen | Frontend Engineer | 5 | 1000 | 5000
4A-09 | 4A | Manual-Review Routing (Fail Path) | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4A-10 | 4A | Phase 4a Test Pass | QA Engineer | 4 | 900 | 3600
4A-11 | 4A | Phase 4a Demo & Stakeholder Review | Project Manager | 1 | 1050 | 1050
4B-01 | 4B | PA Aggregation FHIR Server Provisioning | Data/Integration Engineer | 3 | 1100 | 3300
4B-02 | 4B | EMR US Core v3 Pull Service | Backend/FHIR Engineer 2 | 5 | 1100 | 5500
4B-03 | 4B | Patient Access API Pull Service | Backend/FHIR Engineer 2 | 5 | 1100 | 5500
4B-04 | 4B | Merge, Priority & Provenance Logic | Data/Integration Engineer | 5 | 1100 | 5500
4B-05 | 4B | Questionnaire Package Retrieval | Backend/FHIR Engineer 1 | 5 | 1100 | 5500
4B-06 | 4B | DTR SMART App Launch | Frontend Engineer | 4 | 1000 | 4000
4B-07 | 4B | CQL Execution Engine Integration | Backend/FHIR Engineer 1 | 6 | 1100 | 6600
4B-08 | 4B | Medical Necessity Tree UI | Frontend Engineer | 6 | 1000 | 6000
4B-09 | 4B | CDex Attachment Upload | Backend/FHIR Engineer 2 | 5 | 1100 | 5500
4B-10 | 4B | Re-run Match on Upload | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4B-11 | 4B | Phase 4b Test Pass | QA Engineer | 5 | 900 | 4500
4B-12 | 4B | Phase 4b Demo & Stakeholder Review | Project Manager | 1 | 1050 | 1050
4C-01 | 4C | PASBundle Assembly Service | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
4C-02 | 4C | Claim/$submit Integration | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
4C-03 | 4C | EDI Translator (X12 278/275) | Backend/FHIR Engineer 2 | 6 | 1100 | 6600
4C-04 | 4C | Channel Selection Logic | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4C-05 | 4C | Review & Submit UI Screen | Frontend Engineer | 4 | 1000 | 4000
4C-06 | 4C | PA Number & Case Record Generation | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4C-07 | 4C | PA Portal Status Vocabulary Update | Frontend Engineer | 3 | 1000 | 3000
4C-08 | 4C | Phase 4c Test Pass | QA Engineer | 4 | 900 | 3600
4D-01 | 4D | Evidence Record PDF Generator | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4D-02 | 4D | FHIR Subscription (rest-hook) Listener | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
4D-03 | 4D | Claim/$inquiry Manual Fallback | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4D-04 | 4D | ClaimResponse Processing & Status Mapping | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
4D-05 | 4D | Case Detail / Timeline UI | Frontend Engineer | 5 | 1000 | 5000
4D-06 | 4D | Resubmit vs. Update/Cancel Logic | Backend/FHIR Engineer 2 | 3 | 1100 | 3300
4D-07 | 4D | Phase 4d Test Pass | QA Engineer | 4 | 900 | 3600
4E-01 | 4E | Batch Worklist Queue Service | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4E-02 | 4E | Back-Office Worklist UI | Frontend Engineer | 5 | 1000 | 5000
4E-03 | 4E | Staff Assignment & Override Workflow | Backend/FHIR Engineer 2 | 3 | 1100 | 3300
4E-04 | 4E | Audit Trail for Manual Overrides | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4E-05 | 4E | Phase 4e Test Pass | QA Engineer | 3 | 900 | 2700
HD-01 | HD | End-to-End Integration Testing | QA Engineer | 5 | 900 | 4500
HD-02 | HD | Security Review | Security Engineer | 4 | 1250 | 5000
HD-03 | HD | CMS-0057-F Compliance Validation | Product/Clinical SME | 3 | 1300 | 3900
HD-04 | HD | Performance / Load Testing | QA Engineer | 3 | 900 | 2700
HD-05 | HD | UAT with Clinical Stakeholders | Product/Clinical SME | 4 | 1300 | 5200
HD-06 | HD | Production Readiness Review & Go-Live Checklist | Project Manager | 2 | 1050 | 2100
HD-07 | HD | Documentation & Handoff | Tech Lead | 2 | 1450 | 2900
|  | TOTAL |  | 204.5 |  | 221575

## Cost Summary
Cost Summary — Implementation (Build) Cost
Scope: 1 payer set of test profiles is built/tested in Phase 4b; production EMR and payer connection counts are set in Assumptions.
Labor Cost by Role
Role | Person-Days | Cost ($)
Tech Lead | 7.5 | 10875
Backend/FHIR Engineer 1 | 57 | 62700
Backend/FHIR Engineer 2 | 47 | 51700
Data/Integration Engineer | 13 | 14300
Frontend Engineer | 32 | 32000
QA Engineer | 28 | 25200
Security Engineer | 4 | 5000
Product/Clinical SME | 12 | 15600
Project Manager | 4 | 4200
Clinical Policy Reviewer | 0 | 0
Total Labor Cost | 204.5 | 221575
Labor Cost by Phase
Phase | Phase Name | Cost ($)
S0 | Sprint 0 — Foundation & Design Spike | 23275
4A | Phase 4a — CRD Integration & Checklist UI | 43750
4B | Phase 4b — DTR, Aggregation FHIR Server & Necessity Tree UI | 55150
4C | Phase 4c — PAS Submission & Channel Routing | 29300
4D | Phase 4d — Evidence Record & Status Sync | 26200
4E | Phase 4e — Back-Office Batch Worklist | 17600
HD | Hardening — Integration, Security, Compliance, UAT | 26300
Scope Detail — EMR, Payer & Other Endpoints
Item | Quantity | Cost ($, one-time)
EMR connections (additional, beyond base build) | 3 | 105000
Payer connections (production onboarding) | 3 | 60000
UM sub-vendor integrations (Magellan/Prime/Internal-style) | 9 | 72000
EDI clearinghouse connection setup | 1 | 8000
Additional HIE / data-source connections | 0 | 0
Idaho facility rollout (per-site install, one-time) | 18 | 72000
Total EMR / Payer / Endpoint Cost |  | 317000
HIPAA & Compliance Certification
Item | Cost ($, one-time)
HIPAA Risk Assessment & Remediation | 30000
BAA Legal Review & Execution | 5000
SOC 2 Type II — Year 1 (readiness + audit) | 45000
HITRUST CSF Certification (if included) | 0
Total Compliance Cost | 80000
Policy Ingestion & Clinical Review (Intelligent Policy Engine -> DTR Rules)
Metric | Value | Note
Production payer connections | 3 | From Integration Scope — Payer Connections
Policies per payer (initial scope) | 150 | PLACEHOLDER — confirm actual policy library size per payer
Total policies — initial ingestion | 450 | Clinically reviewed once, at launch
Cost per document — initial ingestion | 237.5 | Clinical Policy Reviewer hourly rate x initial review hours
Total Initial Policy Review Cost (one-time) | 106875
Implied Clinical Policy Reviewer FTEs (to clear initial backlog within the build window) | 1.25 | Staffing guide only — see Assumptions
New / revised policies per payer, per year (ongoing) | 30 | Illustrative annual revision rate
Total policies processed — annual (ongoing) | 90 | Feeds the Ongoing Run-Rate tab
Idaho EMR & Facility Rollout
Metric | Value | Note
Total Idaho hospital facilities (all vendors) | 55 | 55 hospitals statewide, incl. 27 critical access hospitals
Facilities in scope for initial deployment | 18 | Epic (7) + Oracle Health/Cerner (2) + MEDITECH (9) -- the 3 confirmed platforms
Cost per facility (one-time) | 4000 | Site go-live: workflow validation, IT coordination, training
Total Facility Rollout Cost (one-time) | 72000
Cost per facility (monthly, ongoing) | 150 | Per-site monitoring, credential rotation, local support
Implementation Cost Build-Up
Category | Cost ($) | Basis
Labor | 221575 | Sum of all 57 task costs (Task Cost Detail)
Infrastructure (build phase) | 28907.8341 | Monthly infra total (selected cloud provider) x build duration in months
Third-Party Licensing (build phase) | 35253.4562 | Milliman + InterQual (pro-rated annual) + EDI translator + watsonx, all x build months
EMR / Payer / Other Endpoint Onboarding | 317000 | See Scope Detail above
HIPAA & Compliance Certification | 80000 | See HIPAA & Compliance Certification above
One-Time Costs (Other) | 68000 | Security penetration test + UAT logistics
Policy Ingestion — Initial Clinical Review | 106875 | Clinical Policy Reviewer sign-off on every policy converted to a DTR rule set at launch — see Assumptions
Infor Cloverleaf Integration Engine (optional) | 234562.212 | One-time implementation + prorated annual license across build months — toggle in Assumptions
CMS-0057-F APIs — Patient/Provider/Payer-to-Payer | 516000 | Patient Access enhancement + Provider Access build + Payer-to-Payer build/consent + prior payer connections — see Assumptions
Subtotal | 1608173.5023
Contingency | 241226.0253 | Contingency % applied to subtotal
TOTAL IMPLEMENTATION COST | 1849399.5276

## Ongoing Run-Rate
Ongoing Run-Rate — Post Go-Live (Steady State)
Monthly and annual operating cost once the solution is live, independent of the one-time build cost.
Category | Monthly ($) | Basis
Infrastructure & Hosting (scaled for production) | 8364 | Build-phase infra monthly total (selected cloud provider) x post-launch scale-up factor
Third-Party Licensing (recurring) | 10500 | Milliman/12 + InterQual/12 + EDI translator + watsonx (post-launch volume)
Backend/FHIR Support Labor | 11935 | Support FTE allocation x daily rate x avg. working days/month
QA Support Labor | 4882.5 | Support FTE allocation x daily rate x avg. working days/month
Additional EMR Connections (maintenance) | 1500 | Additional EMR connections x ongoing monthly rate per connection
Payer Connections (monitoring & fees) | 2250 | Production payer connections x ongoing monthly rate per connection
UM Sub-Vendor Integrations (monitoring & fees) | 2700 | Payer connections x sub-vendors per payer x ongoing monthly rate per sub-vendor
SOC 2 Type II Annual Renewal (amortized monthly) | 2083.3333 | Annual renewal cost spread across 12 months
HITRUST CSF Annual Renewal (amortized monthly, if included) | 0 | Only non-zero if HITRUST is included in Assumptions
Policy Revision — Clinical Review (amortized monthly) | 890.625 | Annual clinical review cost for new/revised payer policies, spread across 12 months
Facility Connectivity (per-install, ongoing) | 2700 | Facilities in scope x monthly cost per facility install (Idaho EMR & Facility Landscape)
Infor Cloverleaf (annual license, amortized monthly, optional) | 8333.3333 | Toggle in Assumptions — alternative/complement to the EDI Clearinghouse/Translator line above
CMS-0057-F APIs — Patient/Provider/Payer-to-Payer (ongoing) | 8200 | Patient Access vendor fee + Provider Access hosting + Payer-to-Payer ops + prior payer connection monitoring
Total Monthly Run-Rate | 64338.7917
Total Annual Run-Rate | 772065.5