## Assumptions
Prior Authorization Modernization — Cost Model
Assumptions
Prepared for Richard Williams, IBM • July 2026
All figures below are illustrative planning-level placeholders (not quotes) — cells in blue are inputs. Replace with actual rates/quotes when known.
Labor Rates ($ / day, blended)
Role | Daily Rate ($) |  | Note
Tech Lead | 1450 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Backend/FHIR Engineer 1 | 1100 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Backend/FHIR Engineer 2 | 1100 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Data/Integration Engineer | 1100 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Frontend Engineer | 1000 |  | Illustrative U.S. blended consulting rate — replace with actual rate
QA Engineer | 900 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Security Engineer | 1250 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Product/Clinical SME | 1300 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Project Manager | 1050 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Clinical Policy Reviewer | 950 |  | Illustrative U.S. blended consulting rate — replace with actual rate
Schedule Assumptions
Working days per week | 5 |  | Standard 5-day work week
Build duration (weeks) | 18 |  | From the Implementation Plan — total project End Week
Avg. working days per month | 21.7 |  | 52 weeks x 5 days / 12 months
Build duration (months) | 4.1475 |  | Calculated from build duration in weeks
Cloud Hosting — Infrastructure (Monthly, USD)
Cloud Provider | AWS |  | Select AWS or Azure — drives the Total Infrastructure cost below
Component | AWS ($/mo) | Azure ($/mo) | Note
Compute — CRD/DTR/PAS microservices | 1400 | 1500 | AWS Fargate (ECS) / Azure Container Apps
Managed FHIR Datastore | 2800 | 3200 | AWS HealthLake / Azure Health Data Services (FHIR service)
PA Aggregation DB & Object Storage | 600 | 650 | RDS Postgres + S3 / Azure Cosmos DB + Blob Storage
DTR SMART App Hosting (CDN) | 300 | 300 | CloudFront + S3 / Azure Static Web Apps + CDN
API Gateway / Load Balancer | 250 | 280 | AWS ALB + API Gateway / Azure API Management
Backup & Disaster Recovery | 400 | 450 | Cross-region backup and point-in-time recovery
Monitoring & Logging | 300 | 320 | Amazon CloudWatch / Azure Monitor
Security — WAF, Key Mgmt, Secrets | 250 | 270 | AWS WAF + KMS / Azure Front Door WAF + Key Vault
Total Infrastructure (Monthly, Selected Provider) | 6300
Integration Scope — EMR Connections
EMR connections included in base build | 1 |  | Base build (Phase 4b) integrates one EMR via generic US Core v3
Total EMR connections in scope | 4 |  | Idaho: Epic + Oracle Health/Cerner + MEDITECH + 1 platform for remaining independent/CAH facilities — see Idaho EMR & Facility Landscape below
Cost per additional EMR connection (one-time) | 35000 |  | Vendor app-store certification (e.g., Epic App Orchard), sandbox integration & testing
Cost per additional EMR connection (monthly, ongoing) | 500 |  | Ongoing vendor fees + maintenance per connected EMR
Additional EMR connections | 3 |  | Total minus what the base build already includes
Idaho EMR & Facility Landscape
Research-based facility counts per EMR platform, current as of July 2026 (see chat for sources). The ‘Platform’ rows above cover the one-time engineering cost to integrate with each EMR VENDOR once; every individual hospital/facility running that vendor still needs its own site rollout — that per-facility cost is priced separately below.
EMR Platform | Idaho Hospital Facilities |  | Note / Source
Epic | 7 |  | St. Luke's Health System (6 hospitals) + Kootenai Health (1) — both confirmed Epic
Oracle Health / Cerner | 2 |  | Saint Alphonsus Idaho facilities (Boise + Nampa); Trinity Health parent may migrate to Epic over time — monitor
MEDITECH | 9 |  | HCA/Eastern Idaho Regional Medical Center (1, confirmed Expanse) + ~8 estimated critical access hospitals (MEDITECH targets 1-200 bed facilities)
Other / Unconfirmed (CPSI, Cerner CommunityWorks, athenahealth, independent) | 37 |  | Remaining Idaho hospitals, mostly small critical access facilities — vendor mix not individually confirmed, needs direct payer/facility outreach
Total Idaho Hospital Facilities | 55 |  | Idaho: 55 hospitals total, incl. 27 CMS-designated critical access hospitals (Becker's Hospital Review / RHT Compass, 2025)
Facilities in scope for initial deployment | 18 |  | Default = the 3 confirmed platforms only (Epic 7 + Oracle Health/Cerner 2 + MEDITECH 9); expand once the 'Other/Unconfirmed' 37 are vendor-confirmed
Cost per facility install (one-time) | 4000 |  | Site-specific go-live: order-set/workflow validation, local IT coordination, provider orientation — much lighter than the platform-level build
Cost per facility install (monthly, ongoing) | 150 |  | Per-site monitoring, credential rotation, minor local config support
Total Facility Rollout Cost (one-time) | 72000
Total Facility Connectivity Cost (monthly, ongoing) | 2700
Integration Scope — Payer Connections
Production payer connections in scope | 3 |  | Each payer requires its own CRD/DTR/PAS endpoint onboarding & trading partner agreement
Cost per payer onboarding (one-time) | 20000 |  | Endpoint conformance testing, EDI 278/275 mapping validation, trading partner agreement, go-live certification
Cost per payer connection (monthly, ongoing) | 750 |  | Monitoring + per-payer clearinghouse/EDI fees
Other Endpoints
EDI clearinghouse connection setup (one-time) | 8000 |  | One-time trading-partner setup, distinct from the monthly translator fee below
Additional HIE / data-source connections | 0 |  | State HIE or other external clinical data source — optional, defaults to none
Cost per additional HIE connection (one-time) | 15000 |  | Only applies if the count above is > 0
Third-Party Licensing
Item | Cost |  | Note
Milliman Care Guidelines API (annual) | 60000 |  | Illustrative annual license fee — confirm with vendor
InterQual API (annual) | 55000 |  | Illustrative annual license fee — confirm with vendor
EDI Clearinghouse / Translator (monthly) | 1500 |  | Transaction-based estimate for X12 278/275
watsonx / GenAI Usage — Build Phase (monthly) | 2000 |  | Lower volume during build/test
watsonx / GenAI Usage — Post-Launch (monthly) | 4000 |  | Estimated production volume
HIPAA & Compliance Certification
HIPAA Risk Assessment & Gap Remediation (one-time) | 30000 |  | Third-party HIPAA Security Rule risk assessment ahead of go-live
BAA Legal Review & Execution (one-time) | 5000 |  | Legal review/execution of Business Associate Agreements with EMR/payer partners
SOC 2 Type II Readiness + Audit — Year 1 (one-time) | 45000 |  | Common trust requirement for payer/EMR trading partners
SOC 2 Type II Annual Renewal (ongoing/year) | 25000 |  | Recurring annual audit after Year 1
Include HITRUST CSF Certification? | No |  | Optional upgrade — only if required by a specific payer/EMR trading partner
HITRUST CSF Certification (one-time) | 120000 |  | Only applied to totals if 'Include HITRUST' above is Yes
HITRUST CSF Annual Renewal (ongoing/year) | 40000 |  | Only applied to totals if 'Include HITRUST' above is Yes
One-Time Costs (Other)
External Security Penetration Test | 25000 |  | One-time, ahead of go-live
UAT Logistics & Clinical SME Stipends | 8000 |  | One-time, hardening sprint
Total One-Time Costs (Other) | 33000
Contingency % | 15% |  | Applied to Labor + Infrastructure + Licensing + Integration + Compliance + One-Time subtotal
Post Go-Live Support (Ongoing, Monthly)
Backend/FHIR Support Engineer allocation (FTE) | 0.5 |  | Ongoing production support
QA Support allocation (FTE) | 0.25 |  | Ongoing regression/monitoring support
Infra scale-up factor, post-launch | 1.2 |  | Applied to build-phase infra monthly total for production load
Policy Ingestion & Clinical Review (Intelligent Policy Engine -> DTR Rules)
Every payer medical policy the Intelligent Policy Engine converts into a DTR Questionnaire+CQL rule set must be clinically reviewed and signed off before use — this section is unscoped in the base 57-task build plan (S0-03 only validates the pipeline on one sample policy) and needs its own headcount and per-document cost.
Policies per payer — initial ingestion scope | 150 |  | PLACEHOLDER — actual policy library size is unknown; confirm the real count with each payer and update this cell
Total policies — initial ingestion | 450 |  | Production payer connections (above) x policies per payer
New / revised policies per payer, per year | 30 |  | Illustrative — payers typically revise ~15-25% of active policies annually plus add new ones
Total policies processed — annual (ongoing) | 90 |  | Production payer connections (above) x new/revised policies per payer per year
Clinical Policy Reviewer hours per working day | 8 |  | Standard full workday
Review hours per document — initial ingestion | 2 |  | Read source policy, verify AI-extracted JSON/Questionnaire/CQL mapping, validate ICD-10/CPT code sets, sign off
Review hours per document — annual revision | 1 |  | Lighter delta-review against an already-approved baseline
Clinical Policy Reviewer hourly rate | 118.75 |  | Clinical Policy Reviewer daily rate (Labor Rates above) / hours per day
Cost per document — initial ingestion | 237.5 |  | Reviewer hourly rate x initial review hours per document
Cost per document — annual revision | 118.75 |  | Reviewer hourly rate x revision review hours per document
Total Initial Policy Review Cost (one-time) | 106875
Total Annual Policy Revision Review Cost (ongoing) | 10687.5
Implied reviewer FTEs to clear initial backlog within build window | 1.25 |  | Total initial review hours / (build weeks x days/week x hours/day) — staffing guide only

## Task Cost Detail
ID | Phase | Task | Owner Role | Person-Days | Daily Rate ($) | Task Cost ($)
S0-01 | S0 | Repo & Environment Review | Tech Lead | 3 | 1450 | 4350
S0-02 | S0 | Cut feature/phase4-crd-dtr-pas-integration Branch | Tech Lead | 0.5 | 1450 | 725
S0-03 | S0 | Intelligent Policy Engine Schema Spike | Data/Integration Engineer | 5 | 1100 | 5500
S0-04 | S0 | Milliman/InterQual API Access & Licensing Confirmation | Product/Clinical SME | 3 | 1300 | 3900
S0-05 | S0 | Payer Endpoint Directory & Capability Schema | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
S0-06 | S0 | CI/CD & Environment Setup | Tech Lead | 2 | 1450 | 2900
S0-07 | S0 | Confidence-Threshold Policy Workshop | Product/Clinical SME | 2 | 1300 | 2600
4A-01 | 4A | CDS Hooks Client | Backend/FHIR Engineer 1 | 5 | 1100 | 5500
4A-02 | 4A | Prior Auth Service Orchestrator (Skeleton) | Backend/FHIR Engineer 1 | 5 | 1100 | 5500
4A-03 | 4A | Eligibility & Enrollment Check | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4A-04 | 4A | Provider Network Status Check | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4A-05 | 4A | Milliman/InterQual Guideline Check | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4A-06 | 4A | PA-Required Policy Lookup | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
4A-07 | 4A | CDS Card / Coverage Information Builder | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
4A-08 | 4A | CRD Checklist UI Screen | Frontend Engineer | 5 | 1000 | 5000
4A-09 | 4A | Manual-Review Routing (Fail Path) | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4A-10 | 4A | Phase 4a Test Pass | QA Engineer | 4 | 900 | 3600
4A-11 | 4A | Phase 4a Demo & Stakeholder Review | Project Manager | 1 | 1050 | 1050
4B-01 | 4B | PA Aggregation FHIR Server Provisioning | Data/Integration Engineer | 3 | 1100 | 3300
4B-02 | 4B | EMR US Core v3 Pull Service | Backend/FHIR Engineer 2 | 5 | 1100 | 5500
4B-03 | 4B | Patient Access API Pull Service | Backend/FHIR Engineer 2 | 5 | 1100 | 5500
4B-04 | 4B | Merge, Priority & Provenance Logic | Data/Integration Engineer | 5 | 1100 | 5500
4B-05 | 4B | Questionnaire Package Retrieval | Backend/FHIR Engineer 1 | 5 | 1100 | 5500
4B-06 | 4B | DTR SMART App Launch | Frontend Engineer | 4 | 1000 | 4000
4B-07 | 4B | CQL Execution Engine Integration | Backend/FHIR Engineer 1 | 6 | 1100 | 6600
4B-08 | 4B | Medical Necessity Tree UI | Frontend Engineer | 6 | 1000 | 6000
4B-09 | 4B | CDex Attachment Upload | Backend/FHIR Engineer 2 | 5 | 1100 | 5500
4B-10 | 4B | Re-run Match on Upload | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4B-11 | 4B | Phase 4b Test Pass | QA Engineer | 5 | 900 | 4500
4B-12 | 4B | Phase 4b Demo & Stakeholder Review | Project Manager | 1 | 1050 | 1050
4C-01 | 4C | PASBundle Assembly Service | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
4C-02 | 4C | Claim/$submit Integration | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
4C-03 | 4C | EDI Translator (X12 278/275) | Backend/FHIR Engineer 2 | 6 | 1100 | 6600
4C-04 | 4C | Channel Selection Logic | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4C-05 | 4C | Review & Submit UI Screen | Frontend Engineer | 4 | 1000 | 4000
4C-06 | 4C | PA Number & Case Record Generation | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4C-07 | 4C | PA Portal Status Vocabulary Update | Frontend Engineer | 3 | 1000 | 3000
4C-08 | 4C | Phase 4c Test Pass | QA Engineer | 4 | 900 | 3600
4D-01 | 4D | Evidence Record PDF Generator | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4D-02 | 4D | FHIR Subscription (rest-hook) Listener | Backend/FHIR Engineer 1 | 4 | 1100 | 4400
4D-03 | 4D | Claim/$inquiry Manual Fallback | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4D-04 | 4D | ClaimResponse Processing & Status Mapping | Backend/FHIR Engineer 1 | 3 | 1100 | 3300
4D-05 | 4D | Case Detail / Timeline UI | Frontend Engineer | 5 | 1000 | 5000
4D-06 | 4D | Resubmit vs. Update/Cancel Logic | Backend/FHIR Engineer 2 | 3 | 1100 | 3300
4D-07 | 4D | Phase 4d Test Pass | QA Engineer | 4 | 900 | 3600
4E-01 | 4E | Batch Worklist Queue Service | Backend/FHIR Engineer 2 | 4 | 1100 | 4400
4E-02 | 4E | Back-Office Worklist UI | Frontend Engineer | 5 | 1000 | 5000
4E-03 | 4E | Staff Assignment & Override Workflow | Backend/FHIR Engineer 2 | 3 | 1100 | 3300
4E-04 | 4E | Audit Trail for Manual Overrides | Backend/FHIR Engineer 1 | 2 | 1100 | 2200
4E-05 | 4E | Phase 4e Test Pass | QA Engineer | 3 | 900 | 2700
HD-01 | HD | End-to-End Integration Testing | QA Engineer | 5 | 900 | 4500
HD-02 | HD | Security Review | Security Engineer | 4 | 1250 | 5000
HD-03 | HD | CMS-0057-F Compliance Validation | Product/Clinical SME | 3 | 1300 | 3900
HD-04 | HD | Performance / Load Testing | QA Engineer | 3 | 900 | 2700
HD-05 | HD | UAT with Clinical Stakeholders | Product/Clinical SME | 4 | 1300 | 5200
HD-06 | HD | Production Readiness Review & Go-Live Checklist | Project Manager | 2 | 1050 | 2100
HD-07 | HD | Documentation & Handoff | Tech Lead | 2 | 1450 | 2900
|  | TOTAL |  | 204.5 |  | 221575

## Cost Summary
Cost Summary — Implementation (Build) Cost
Scope: 1 payer set of test profiles is built/tested in Phase 4b; production EMR and payer connection counts are set in Assumptions.
Labor Cost by Role
Role | Person-Days | Cost ($)
Tech Lead | 7.5 | 10875
Backend/FHIR Engineer 1 | 57 | 62700
Backend/FHIR Engineer 2 | 47 | 51700
Data/Integration Engineer | 13 | 14300
Frontend Engineer | 32 | 32000
QA Engineer | 28 | 25200
Security Engineer | 4 | 5000
Product/Clinical SME | 12 | 15600
Project Manager | 4 | 4200
Clinical Policy Reviewer | 0 | 0
Total Labor Cost | 204.5 | 221575
Labor Cost by Phase
Phase | Phase Name | Cost ($)
S0 | Sprint 0 — Foundation & Design Spike | 23275
4A | Phase 4a — CRD Integration & Checklist UI | 43750
4B | Phase 4b — DTR, Aggregation FHIR Server & Necessity Tree UI | 55150
4C | Phase 4c — PAS Submission & Channel Routing | 29300
4D | Phase 4d — Evidence Record & Status Sync | 26200
4E | Phase 4e — Back-Office Batch Worklist | 17600
HD | Hardening — Integration, Security, Compliance, UAT | 26300
Scope Detail — EMR, Payer & Other Endpoints
Item | Quantity | Cost ($, one-time)
EMR connections (additional, beyond base build) | 3 | 105000
Payer connections (production onboarding) | 3 | 60000
EDI clearinghouse connection setup | 1 | 8000
Additional HIE / data-source connections | 0 | 0
Idaho facility rollout (per-site install, one-time) | 18 | 72000
Total EMR / Payer / Endpoint Cost |  | 245000
HIPAA & Compliance Certification
Item | Cost ($, one-time)
HIPAA Risk Assessment & Remediation | 30000
BAA Legal Review & Execution | 5000
SOC 2 Type II — Year 1 (readiness + audit) | 45000
HITRUST CSF Certification (if included) | 0
Total Compliance Cost | 80000
Policy Ingestion & Clinical Review (Intelligent Policy Engine -> DTR Rules)
Metric | Value | Note
Production payer connections | 3 | From Integration Scope — Payer Connections
Policies per payer (initial scope) | 150 | PLACEHOLDER — confirm actual policy library size per payer
Total policies — initial ingestion | 450 | Clinically reviewed once, at launch
Cost per document — initial ingestion | 237.5 | Clinical Policy Reviewer hourly rate x initial review hours
Total Initial Policy Review Cost (one-time) | 106875
Implied Clinical Policy Reviewer FTEs (to clear initial backlog within the build window) | 1.25 | Staffing guide only — see Assumptions
New / revised policies per payer, per year (ongoing) | 30 | Illustrative annual revision rate
Total policies processed — annual (ongoing) | 90 | Feeds the Ongoing Run-Rate tab
Idaho EMR & Facility Rollout
Metric | Value | Note
Total Idaho hospital facilities (all vendors) | 55 | 55 hospitals statewide, incl. 27 critical access hospitals
Facilities in scope for initial deployment | 18 | Epic (7) + Oracle Health/Cerner (2) + MEDITECH (9) -- the 3 confirmed platforms
Cost per facility (one-time) | 4000 | Site go-live: workflow validation, IT coordination, training
Total Facility Rollout Cost (one-time) | 72000
Cost per facility (monthly, ongoing) | 150 | Per-site monitoring, credential rotation, local support
Implementation Cost Build-Up
Category | Cost ($) | Basis
Labor | 221575 | Sum of all 57 task costs (Task Cost Detail)
Infrastructure (build phase) | 26129.0323 | Monthly infra total (selected cloud provider) x build duration in months
Third-Party Licensing (build phase) | 54262.6728 | Milliman + InterQual (pro-rated annual) + EDI translator + watsonx, all x build months
EMR / Payer / Other Endpoint Onboarding | 245000 | See Scope Detail above
HIPAA & Compliance Certification | 80000 | See HIPAA & Compliance Certification above
One-Time Costs (Other) | 33000 | Security penetration test + UAT logistics
Policy Ingestion — Initial Clinical Review | 106875 | Clinical Policy Reviewer sign-off on every policy converted to a DTR rule set at launch — see Assumptions
Subtotal | 766841.7051
Contingency | 115026.2558 | Contingency % applied to subtotal
TOTAL IMPLEMENTATION COST | 881867.9608

## Ongoing Run-Rate
Ongoing Run-Rate — Post Go-Live (Steady State)
Monthly and annual operating cost once the solution is live, independent of the one-time build cost.
Category | Monthly ($) | Basis
Infrastructure & Hosting (scaled for production) | 7560 | Build-phase infra monthly total (selected cloud provider) x post-launch scale-up factor
Third-Party Licensing (recurring) | 15083.3333 | Milliman/12 + InterQual/12 + EDI translator + watsonx (post-launch volume)
Backend/FHIR Support Labor | 11935 | Support FTE allocation x daily rate x avg. working days/month
QA Support Labor | 4882.5 | Support FTE allocation x daily rate x avg. working days/month
Additional EMR Connections (maintenance) | 1500 | Additional EMR connections x ongoing monthly rate per connection
Payer Connections (monitoring & fees) | 2250 | Production payer connections x ongoing monthly rate per connection
SOC 2 Type II Annual Renewal (amortized monthly) | 2083.3333 | Annual renewal cost spread across 12 months
HITRUST CSF Annual Renewal (amortized monthly, if included) | 0 | Only non-zero if HITRUST is included in Assumptions
Policy Revision — Clinical Review (amortized monthly) | 890.625 | Annual clinical review cost for new/revised payer policies, spread across 12 months
Facility Connectivity (per-install, ongoing) | 2700 | Facilities in scope x monthly cost per facility install (Idaho EMR & Facility Landscape)
Total Monthly Run-Rate | 48884.7917
Total Annual Run-Rate | 586617.5