## Read Me
RHTP Modular Implementation & Cost Model
Companion workbook to “RHTP Modular Implementation & Cost Strategy” ¦ Prepared by Rick Williams, IBM RHTP Team ¦ July 2026
Purpose and scope
This workbook models the cost to build and run RHTP as a modular platform, sized against a single
illustrative reference deployment: one state Medicaid MCO / county program, roughly 300,000 covered lives,
phased from a single-cohort pilot to statewide scale. Every dollar figure, rate, and effort estimate is a
placeholder for your team to replace with real IBM rate-card figures and actual client scope — the value of
this workbook is the structure (modules, phasing, formulas), not the specific numbers.
How the sheets fit together
Rate Card — Illustrative onshore vs. offshore blended hourly rates by role. Replace with the real IBM rate card.
Assumptions — Global levers: hours per FTE-month, blended company rates, and default onshore/offshore mix by module type.
Module Build Cost — All 23 build modules (core platform, persona experiences, data connectors) with effort (FTE-months), onshore/offshore mix, and computed build cost.
Phase Summary — Rolls module costs up into the four delivery phases, with duration and average concurrent team size.
Run & Maintain — Steady-state annual operating cost: support team, cloud/infrastructure, and software licensing, plus a ramp estimate for the Phase 1 pilot period.
ROI Illustration — A worked example of how Phase 1 investment could be weighed against avoided-utilization savings for a pilot cohort. Methodology, not a projection.
Timeline — Phase start/duration/end in months, used to build the Gantt-style roadmap graphic in the companion Word document.
Color legend
Blue text = an input or editable assumption — change this.
Black text = a formula — do not overwrite with a hardcoded number.
Green text = a link that pulls a value from another sheet.
Yellow fill = a key assumption you should review and likely replace before this leaves IBM.
All figures are illustrative placeholders prepared for internal strategy discussion. Validate with IBM Consulting's actual rate card, delivery estimating standards, and the target client's real population and contract scope before external use.

## Rate Card
Illustrative Role Rate Card (Loaded Hourly, USD)
Placeholder rates — replace with the current IBM Consulting rate card for the engaged geography and labor category.
Role | Onshore Rate ($/hr) | Offshore Rate ($/hr) | Notes
Engagement / Program Lead | 220 | 70 | Overall delivery lead; typically onshore-heavy
Solution Architect (FHIR / Knowledge Graph) | 245 | 85 | Core platform architecture
AI / Agent Orchestration Engineer | 210 | 75 | Builds and tunes the agent orchestration layer
Data / Integration Engineer | 185 | 60 | Connectors, ETL, FHIR Bulk Data pipelines
Platform / DevSecOps Engineer | 190 | 65 | Hosting, CI/CD, observability, security controls
UX / Product Designer | 165 | 55 | Persona-specific experience design
QA / Test Engineer | 150 | 45 | Functional, integration, and regression testing
Clinical / Business SME | 200 | n/a | Care management & SDOH subject-matter input; typically onshore only
Change Management / Training | 160 | 50 | End-user adoption, training materials, rollout support
Support Analyst (L1/L2) | 130 | 40 | Steady-state helpdesk and monitoring

## Assumptions
Global Assumptions
Levers used throughout the Module Build Cost, Phase Summary, and Run & Maintain sheets.
Assumption | Value | Note
Hours per FTE-month | 160 | Standard full-time monthly billable hours
Months per year | 12
Company blended rates (used for module-level build costing)
Blended onshore rate ($/hr) | 195 | Approximate team-weighted average across Rate Card roles; refine once the Phase 1 team roster is set
Blended offshore rate ($/hr) | 65
Default onshore mix by module type (editable per-row in Module Build Cost)
Core Platform modules — % onshore | 65% | Architecture-heavy; more senior, onshore-weighted
Persona Module modules — % onshore | 45%
Data Connector modules — % onshore | 35% | Integration engineering can be leveraged more heavily offshore
AI-assisted (Bob/Claude) build acceleration by module type
Core Platform modules — Bob hours as % of dev-team hours | 50% | Architecture-, security-, and compliance-heavy; human review/validation remains the bottleneck even with AI-assisted coding
Persona Module modules — Bob hours as % of dev-team hours | 30% | UI/workflow-heavy screens; AI pair-development accelerates scaffolding, forms, and CRUD logic significantly
Data Connector modules — Bob hours as % of dev-team hours | 35% | Mapping/ETL code generates quickly with AI; hours remain bounded by testing against real source systems

## Module Build Cost
Module Build Cost — All Phases
Effort (FTE-months) and onshore/offshore mix are inputs; hours and cost columns are formulas. Sized against the reference 300K-covered-lives deployment.
# | Module | Category | Phase | FTE-Months | % Onshore | % Offshore | Onshore Hrs | Offshore Hrs | Onshore Cost | Offshore Cost | Total Build Cost
1 | C1. FHIR-Native Integration & Ingestion Layer (real-time API gateway + batch ETL / Bulk Data) | Core Platform | 1 | 8 | 65% | 35% | 832 | 448 | 162240 | 29120 | 191360
2 | C2. Knowledge Graph & Master Person Index | Core Platform | 1 | 6 | 65% | 35% | 624 | 336 | 121680 | 21840 | 143520
3 | C3. Consent & Governance Engine (FHIR Consent, purpose-of-use, audit) | Core Platform | 1 | 4 | 65% | 35% | 416 | 224 | 81120 | 14560 | 95680
4 | C4. Agent Orchestration Engine (reasoning, workflow, guardrails) | Core Platform | 1 | 10 | 65% | 35% | 1040 | 560 | 202800 | 36400 | 239200
5 | C5. Identity, Security & Platform Ops (IAM, hosting, DevSecOps, observability) | Core Platform | 1 | 5 | 65% | 35% | 520 | 280 | 101400 | 18200 | 119600
6 | P1. Care Manager Workspace (worklist, gaps-in-care, root-cause views) | Persona Module | 1 | 5 | 45% | 55% | 360 | 440 | 70200 | 28600 | 98800
7 | P2. Case Manager / Care Coordinator Configuration (workflow variant) | Persona Module | 1 | 1.5 | 45% | 55% | 108 | 132 | 21060 | 8580 | 29640
8 | P5. Community-Based Organization (CBO) Referral & Closed-Loop Module | Persona Module | 1 | 3 | 45% | 55% | 216 | 264 | 42120 | 17160 | 59280
9 | D1. Clinical EHR FHIR Connector | Data Connector | 1 | 3 | 35% | 65% | 168 | 312 | 32760 | 20280 | 53040
10 | D2. Claims & Eligibility (X12 837/835) Connector | Data Connector | 1 | 3 | 35% | 65% | 168 | 312 | 32760 | 20280 | 53040
11 | D3. SDOH Manual Assessment Intake (PRAPARE / AHC HRSN) | Data Connector | 1 | 2 | 35% | 65% | 112 | 208 | 21840 | 13520 | 35360
12 | D5. CBO / Community Referral Network Connector | Data Connector | 1 | 2 | 35% | 65% | 112 | 208 | 21840 | 13520 | 35360
13 | P3. Provider & Specialist Module (SMART on FHIR, EHR-embedded) | Persona Module | 2 | 4 | 45% | 55% | 288 | 352 | 56160 | 22880 | 79040
14 | P4. Resident / Consumer Engagement (portal + SMS, tiered autonomy) | Persona Module | 2 | 4 | 45% | 55% | 288 | 352 | 56160 | 22880 | 79040
15 | D4. Behavioral Health + 42 CFR Part 2 Consent Connector | Data Connector | 2 | 3 | 35% | 65% | 168 | 312 | 32760 | 20280 | 53040
16 | D6. Patient Access API Connector (real-time, consent-based) | Data Connector | 2 | 3 | 35% | 65% | 168 | 312 | 32760 | 20280 | 53040
17 | D7. Provider Access API Connector (real-time) | Data Connector | 2 | 3 | 35% | 65% | 168 | 312 | 32760 | 20280 | 53040
18 | P6. County / MCO Program Administrator Analytics | Persona Module | 3 | 5 | 45% | 55% | 360 | 440 | 70200 | 28600 | 98800
19 | P7. RHTP Director Command Center (cross-program oversight & admin) | Persona Module | 3 | 4 | 45% | 55% | 288 | 352 | 56160 | 22880 | 79040
20 | P8. Value-Based Care / Contract Management Module | Persona Module | 3 | 6 | 45% | 55% | 432 | 528 | 84240 | 34320 | 118560
21 | D8. Medicaid Enterprise Data Warehouse (EDW) Connector | Data Connector | 3 | 4 | 35% | 65% | 224 | 416 | 43680 | 27040 | 70720
22 | D9. All-Payer Claims Database (APCD) Connector | Data Connector | 3 | 4 | 35% | 65% | 224 | 416 | 43680 | 27040 | 70720
23 | D10. Public Health Connector (Immunization IIS + Vital Records) | Data Connector | 3 | 3 | 35% | 65% | 168 | 312 | 32760 | 20280 | 53040
| TOTAL — ALL PHASES |  |  | 95.5 |  |  | 7452 | 7828 | 1453140 | 508820 | 1961960

## Phase Summary
Phase Summary — Cost, Duration, and Team Size
Module costs roll up automatically from the Module Build Cost sheet. Duration and Phase 0 discovery cost are inputs.
Phase | Description | Duration (months) | # Modules | Total FTE-Months | Total Build Cost | Avg. Concurrent FTE
Phase 0 | Discovery & Foundation Setup (environment, security baseline, cohort selection, integration design) | 1.5 | n/a — fixed-scope | n/a | 150000 | n/a
Phase 1 | MVP / First Value — core platform + Care Manager & CBO workflow + 4 priority connectors, one high-risk cohort | 3.5 | 12 | 52.5 | 1153880 | 15
Phase 2 | Expand Reach & Real-Time — Provider & Resident modules, BH connector, Patient/Provider Access APIs | 3 | 5 | 17 | 317200 | 5.6667
Phase 3 | Program & Population Scale — county/MCO analytics, RHTP Director console, VBC module, EDW/APCD/public health | 6 | 6 | 26 | 490880 | 4.3333
TOTAL |  | 14 | 23 | 95.5 | 2111960
Note on F5: Fixed discovery-phase cost input (not derived from module list) — planning, environment stand-up, security/compliance baseline, cohort & priority-connector selection.

## Run & Maintain
Annual Run & Maintain Cost — Steady State
Steady-state support team once all phases are live, plus infrastructure and licensing. Rates link to the Rate Card sheet.
Role | FTE | % Onshore | Onshore Rate | Offshore Rate | Annual Hours | Annual Labor Cost
Platform / DevSecOps Engineer | 1.5 | 40% | 190 | 65 | 2880 | 331200
Data / Integration Engineer | 1.5 | 30% | 185 | 60 | 2880 | 280800
AI / Agent Orchestration Engineer | 1 | 60% | 210 | 75 | 1920 | 299520
QA / Test Engineer | 0.5 | 20% | 150 | 45 | 960 | 63360
Support Analyst (L1/L2) | 1.5 | 10% | 130 | 40 | 2880 | 141120
Engagement / Program Lead | 0.5 | 100% | 220 | 70 | 960 | 211200
Clinical / Business SME | 0.25 | 100% | 200 | n/a | 480 | 96000
Subtotal — Steady-State Labor | [5 empty] | 1423200
Infrastructure, Cloud & Licensing
Item | Annual Cost | Note
Cloud hosting & compute (incl. agent/LLM inference) | 600000 | $50K/month placeholder — replace with real workload sizing
FHIR server, knowledge graph DB & integration middleware licensing | 180000 | Illustrative annual license/subscription placeholder
Monitoring, security & observability tooling | 70000 | Illustrative annual placeholder
Subtotal — Infrastructure & Licensing | 850000
TOTAL ANNUAL RUN COST — STEADY STATE | 2273200
Phase 1 pilot ramp — % of steady-state run cost | 40% | Smaller team, one cohort, fewer connectors live during Phase 1
Phase 1 partial-year run cost | 909280

## ROI Illustration
Phase 1 ROI Illustration — Worked Example
A methodology, not a projection: shows how Phase 1 investment could be weighed against avoided-utilization savings for a defined pilot cohort. Replace every blue input with the target program's real baseline data.
Input | Value | Note
Pilot cohort size (members) | 7500 | Illustrative high-risk / high-SDOH-need cohort within the reference deployment
Baseline avoidable ED visits per member per year | 0.35 | Illustrative literature-informed placeholder — replace with the program's real baseline
Average avoidable cost per ED visit ($) | 1800 | Illustrative placeholder
Target reduction in avoidable utilization | 10% | Illustrative, directional — needs validation against comparable care-coordination programs
Calculated | Value | Formula logic
Baseline avoidable ED visits (cohort) | 2625 | Cohort size × baseline rate
Avoided visits at target reduction | 262.5 | Baseline visits × target reduction %
Gross annual avoided-cost savings | 472500 | Avoided visits × avg cost per visit
Phase 1 build cost (link) | 1153880 | From Phase Summary
Phase 1 partial-year run cost (link) | 909280 | From Run & Maintain
Total Phase 1 investment | 2063160 | Build + partial-year run
Simple payback (years, illustrative) | 4.3665 | Phase 1 investment ÷ gross annual savings
At full population scale (illustrative)
Population scale factor at full rollout (× pilot cohort) | 4 | E.g., pilot cohort expands from ~7,500 to ~30,000 high-risk members across the full reference population
Full-scale gross annual avoided-cost savings | 1890000 | Phase 1 pilot savings × scale factor
Total platform investment (build, all phases + Phase 0) | 2111960 | From Phase Summary total
Plus one year steady-state run cost | 2273200 | From Run & Maintain total
Total investment through Year 1 at full scale | 4385160 | Build (all phases) + one year of run
Simple payback at full scale (years, illustrative) | 2.3202 | Full-scale investment ÷ full-scale annual savings
This is a directional planning tool, not a savings guarantee. Validate baseline utilization, avoidable-cost, and expected-reduction assumptions against the target program's actual claims history before using these numbers externally.
Note on A20: Phase 1 investment funds the reusable core platform, not just the pilot cohort — so payback improves once that platform serves the full population without being rebuilt.

## Timeline
Delivery Timeline (Months from Kickoff)
Feeds the roadmap graphic in the companion Word document. Durations link to Phase Summary.
Phase | Description | Start Month | Duration (months) | End Month
Phase 0 | Discovery & Foundation Setup (environment, security baseline, cohort selection, integration design) | 0 | 1.5 | 1.5
Phase 1 | MVP / First Value — core platform + Care Manager & CBO workflow + 4 priority connectors, one high-risk cohort | 1.5 | 3.5 | 5
Phase 2 | Expand Reach & Real-Time — Provider & Resident modules, BH connector, Patient/Provider Access APIs | 5 | 3 | 8
Phase 3 | Program & Population Scale — county/MCO analytics, RHTP Director console, VBC module, EDW/APCD/public health | 8 | 6 | 14
First meaningful ROI signal targeted during Phase 1 / early Phase 2 (approx. months 5–9) — well before full Phase 3 population scale.

## Approach B - Partner Model
Approach B — Consulting Asset + Ecosystem Partner Model
Same 23 modules. “Partner leverage %” estimates the effort avoided by integrating an established partner platform (e.g., Unite Us for CBO/community referral, an Infor Cloverleaf-class integration engine for clinical/claims interfaces) via time-boxed “connect-a-thon” sprints instead of custom-building. Core IP modules (knowledge graph, agent orchestration) keep low leverage on purpose — that's what stays IBM-differentiated.
# | Module | Category | Phase | Approach A FTE-Months | Partner Leverage % | Approach B FTE-Months | Approach A Cost | Approach B Cost
1 | C1. FHIR-Native Integration & Ingestion Layer (real-time API gateway + batch ETL / Bulk Data) | Core Platform | 1 | 8 | 35% | 5.2 | 191360 | 124384
2 | C2. Knowledge Graph & Master Person Index | Core Platform | 1 | 6 | 5% | 5.7 | 143520 | 136344
3 | C3. Consent & Governance Engine (FHIR Consent, purpose-of-use, audit) | Core Platform | 1 | 4 | 10% | 3.6 | 95680 | 86112
4 | C4. Agent Orchestration Engine (reasoning, workflow, guardrails) | Core Platform | 1 | 10 | 5% | 9.5 | 239200 | 227240
5 | C5. Identity, Security & Platform Ops (IAM, hosting, DevSecOps, observability) | Core Platform | 1 | 5 | 25% | 3.75 | 119600 | 89700
6 | P1. Care Manager Workspace (worklist, gaps-in-care, root-cause views) | Persona Module | 1 | 5 | 10% | 4.5 | 98800 | 88920
7 | P2. Case Manager / Care Coordinator Configuration (workflow variant) | Persona Module | 1 | 1.5 | 10% | 1.35 | 29640 | 26676
8 | P5. Community-Based Organization (CBO) Referral & Closed-Loop Module | Persona Module | 1 | 3 | 65% | 1.05 | 59280 | 20748
9 | D1. Clinical EHR FHIR Connector | Data Connector | 1 | 3 | 45% | 1.65 | 53040 | 29172
10 | D2. Claims & Eligibility (X12 837/835) Connector | Data Connector | 1 | 3 | 40% | 1.8 | 53040 | 31824
11 | D3. SDOH Manual Assessment Intake (PRAPARE / AHC HRSN) | Data Connector | 1 | 2 | 10% | 1.8 | 35360 | 31824
12 | D5. CBO / Community Referral Network Connector | Data Connector | 1 | 2 | 70% | 0.6 | 35360 | 10608
13 | P3. Provider & Specialist Module (SMART on FHIR, EHR-embedded) | Persona Module | 2 | 4 | 10% | 3.6 | 79040 | 71136
14 | P4. Resident / Consumer Engagement (portal + SMS, tiered autonomy) | Persona Module | 2 | 4 | 15% | 3.4 | 79040 | 67184
15 | D4. Behavioral Health + 42 CFR Part 2 Consent Connector | Data Connector | 2 | 3 | 25% | 2.25 | 53040 | 39780
16 | D6. Patient Access API Connector (real-time, consent-based) | Data Connector | 2 | 3 | 30% | 2.1 | 53040 | 37128
17 | D7. Provider Access API Connector (real-time) | Data Connector | 2 | 3 | 30% | 2.1 | 53040 | 37128
18 | P6. County / MCO Program Administrator Analytics | Persona Module | 3 | 5 | 15% | 4.25 | 98800 | 83980
19 | P7. RHTP Director Command Center (cross-program oversight & admin) | Persona Module | 3 | 4 | 10% | 3.6 | 79040 | 71136
20 | P8. Value-Based Care / Contract Management Module | Persona Module | 3 | 6 | 15% | 5.1 | 118560 | 100776
21 | D8. Medicaid Enterprise Data Warehouse (EDW) Connector | Data Connector | 3 | 4 | 20% | 3.2 | 70720 | 56576
22 | D9. All-Payer Claims Database (APCD) Connector | Data Connector | 3 | 4 | 20% | 3.2 | 70720 | 56576
23 | D10. Public Health Connector (Immunization IIS + Vital Records) | Data Connector | 3 | 3 | 25% | 2.25 | 53040 | 39780
| TOTAL — ALL PHASES |  |  | 95.5 |  | 75.55 | 1961960 | 1564732
Phase rollup — Approach B
Phase | Approach A Cost | Approach B Cost | $ Reduction | % Reduction
Phase 1 | 1153880 | 903552 | 250328 | 21.69%
Phase 2 | 317200 | 252356 | 64844 | 20.44%
Phase 3 | 490880 | 408824 | 82056 | 16.72%
IBM asset investment vs. first-client incremental cost
The reusable IP asset — funded by IBM once, before any client is signed — covers the core platform plus the four most universal Phase 1 connectors and a generic reference Care Manager workspace. Client-specific configuration (case-manager variant, CBO/Unite Us tenant setup, Phase 0 discovery, Phases 2–3) is priced per engagement.
Item | Approach B Cost
IBM asset build (Core Platform + P1 + D1/D2/D3/D5) | 856128
First-client Phase 1 configuration (P2 case-manager variant + P5 Unite Us tenant setup) | 47424
First-client Phase 0 discovery (reduced — partner onboarding playbook already exists) | 110000
First client — total incremental cost to MVP (on top of the asset) | 157424
Approach B — Run & Maintain (Steady State)
Item | Approach B Annual Cost
Support labor (reduced — fewer bespoke connectors to maintain) | 1209720
Cloud hosting & compute | 540000
IBM-built licensing & tooling (reduced scope) | 90000
Monitoring, security & observability | 70000
Partner platform fees (Unite Us network access + Cloverleaf-class engine licensing) | 150000
TOTAL — Approach B Steady State | 2059720
Phase 1 pilot ramp — % of steady-state run cost | 40%
First client Phase 1 partial-year run cost | 823888

## A vs B Comparison
Approach A vs. Approach B — Side-by-Side
Approach A: full custom build. Approach B: reusable IBM IP asset + ecosystem partner connectors (Unite Us, Infor Cloverleaf-class integration engine) via connect-a-thon sprints. All figures link to the sheets above.
Metric | Approach A (Full Custom Build) | Approach B (Asset + Partners) | Difference
Total build cost, all phases | 2111960 | 1674732 | 437228
Phase 0 + Phase 1 / MVP build cost | 1303880 | 1013552 | 290328
IBM upfront asset investment (pre-client) | n/a — not applicable | 856128 | n/a
First client's incremental cost to MVP (on top of the asset) | 1153880 | 157424 | 996456
Total duration, all phases (months) | 14 | 10.5 | 3.5
Time to first live functionality (months) | 5 | 3.75 | 1.25
Annual run cost, steady state | 2273200 | 2059720 | 213480
ROI comparison (same pilot-cohort assumptions as the ROI Illustration tab)
Metric | Approach A | Approach B
Gross annual avoided-cost savings (pilot cohort) | 472500 | 472500
Total Phase 1 investment (asset + first client, build + run ramp) | 2063160 | 1837440
— of which, first client's own incremental cash cost | n/a | 981312
Simple payback — full investment basis (years) | 4.3665 | 3.8888
Simple payback — first client's own cash cost only (years) | n/a — asset not separated under Approach A | 2.0769
Key trade-off: Approach B trades some IBM-owned IP and margin on the CBO/community-referral and interoperability-engine layers for materially lower upfront cost, a faster timeline, and a much lower bar for the first client to say yes. It also introduces partner dependency (roadmap, commercial terms, data-sharing agreements with Unite Us and the integration-engine vendor) as a new risk to manage.

## Module Specification
RHTP Module Specification — Screens, Inputs, Outputs
All 23 modules defined across the cost model and strategy documents (5 Core Platform + 8 Persona + 10 Data Connector). Most Core Platform and Data Connector modules are backend services with no dedicated screen of their own — they surface through the persona screens and an admin/platform console noted below. Two hour-estimate columns have been added: approximate hours for a traditional human development team (linked from the Module Build Cost tab) and approximate hours using Claude ("Bob") as an AI-assisted developer, based on editable acceleration assumptions on the Assumptions tab. Both are illustrative planning estimates, not delivery commitments.
# | Module | Category | Phase | Associated Screen / View | Key Inputs | Key Outputs | Dev Team Development Hours | Bob (Claude) Dev Hours
1 | C1. FHIR-Native Integration & Ingestion Layer | Core Platform | 1 | Admin Console — Data Source Connection Status | Raw source feeds: EHR FHIR APIs, X12 837/835 claims files, batch extracts, real-time API calls (Patient/Provider Access, IIS) | Normalized FHIR R4 resources published to the knowledge graph ingestion queue; connection health/status events | 1280 | 640
2 | C2. Knowledge Graph & Master Person Index | Core Platform | 1 | Backend — surfaces as the “360 Person View” panel embedded in every persona screen | Normalized FHIR resources from all connectors; entity records needing identity resolution | Resolved master person record; relationship graph (person–caregiver–provider–CBO–program); queryable API for every other module | 960 | 480
3 | C3. Consent & Governance Engine | Core Platform | 1 | Consent Management screen (resident-facing) + Admin Console (governance view) | Consent capture events, purpose-of-use tags, program/legal data-sharing agreements | FHIR Consent resources; allow/deny access decisions enforced at query time; audit log entries | 640 | 320
4 | C4. Agent Orchestration Engine | Core Platform | 1 | Backend — surfaces as the “Recommended Actions / Agent Activity” panel on persona dashboards | Knowledge graph state, gap/risk signals, persona workflow rules, governance guardrails from C3 | Recommended actions, auto-generated tasks/referrals, routed notifications, action audit trail | 1600 | 800
5 | C5. Identity, Security & Platform Ops | Core Platform | 1 | Admin Console — Platform Administration screen | User directory, role definitions, security events, deployment artifacts, telemetry | Authenticated sessions, role-based access tokens, uptime/observability dashboards, CI/CD deployments | 800 | 400
6 | P1. Care Manager Workspace | Persona Module | 1 | Care Manager Dashboard / Worklist screen | Person records and relationships (C2), gap-in-care flags, agent recommendations (C4) | Prioritized worklist, updated care plan, tasks/referrals assigned to other stakeholders | 800 | 240
7 | P2. Case Manager / Care Coordinator Configuration | Persona Module | 1 | Case Manager Worklist screen (workflow variant of P1) | Same as P1, filtered/configured for social-services and benefits workflow | Case notes, service plan updates, benefit-program task assignments | 240 | 72
8 | P5. CBO Referral & Closed-Loop Module | Persona Module | 1 | CBO Referral Inbox screen | Referral requests generated by care manager or agent orchestration | Referral acceptance/decline, service-delivery confirmation, closed-loop status back to the knowledge graph | 480 | 144
9 | D1. Clinical EHR FHIR Connector | Data Connector | 1 | Backend — status shown in Admin Console | EHR FHIR API feed (Patient, Condition, Observation, MedicationRequest, CarePlan) | Normalized clinical FHIR resources into C1/C2 | 480 | 168
10 | D2. Claims & Eligibility (X12 837/835) Connector | Data Connector | 1 | Backend — status shown in Admin Console | X12 837/835 claims and eligibility files | Normalized claims/eligibility FHIR resources into C1/C2 | 480 | 168
11 | D3. SDOH Manual Assessment Intake | Data Connector | 1 | SDOH Assessment Entry Form (used by Care Manager and CBO screens) | PRAPARE / AHC HRSN screening responses entered by care coordinators or CBOs | Structured SDOH observations into the knowledge graph | 320 | 112
12 | D5. CBO / Community Referral Network Connector | Data Connector | 1 | Backend — feeds the P5 CBO Referral Inbox screen | CBO network referral and status-update API calls | Referral, Task, and ServiceRequest resources into the knowledge graph | 320 | 112
13 | P3. Provider & Specialist Module | Persona Module | 2 | Provider EHR-embedded panel (SMART on FHIR launch) | SMART on FHIR launch context from the host EHR; SDOH/BH context from the knowledge graph | In-workflow context panel; referral orders and clinical actions written back to the knowledge graph | 640 | 192
14 | P4. Resident / Consumer Engagement | Persona Module | 2 | Resident Portal / Mobile App + SMS | Care plan, consent preferences, task/notification queue from C3/C4 | Resident responses (confirmations, consent choices), self-reported updates | 640 | 192
15 | D4. Behavioral Health + 42 CFR Part 2 Consent Connector | Data Connector | 2 | Backend — status shown in Admin Console | BH EHR/assessment feed, gated by Part 2-compliant consent | Normalized BH FHIR resources into C1/C2, access-gated by C3 | 480 | 168
16 | D6. Patient Access API Connector | Data Connector | 2 | Backend — authorization step shown in Resident Portal (P4) | Real-time payer FHIR API feed, member-authorized via OAuth2 | Live claims/coverage/clinical resources into C1/C2 | 480 | 168
17 | D7. Provider Access API Connector | Data Connector | 2 | Backend — status shown in Admin Console | Real-time payer-to-provider FHIR API feed | Live claims/utilization resources into C1/C2 | 480 | 168
18 | P6. County / MCO Program Administrator Analytics | Persona Module | 3 | Program Analytics Dashboard | Aggregated knowledge graph data plus EDW/APCD extracts | Population-level outcome, utilization, and ROI reports | 800 | 240
19 | P7. RHTP Director Command Center | Persona Module | 3 | Director Command Center screen | Cross-program metrics, platform health telemetry, module usage | Executive oversight views, cross-program configuration controls | 640 | 192
20 | P8. Value-Based Care / Contract Management Module | Persona Module | 3 | VBC Contract Performance Dashboard | Quality measure data, claims/EDW data, contract terms | Contract performance scorecards, shared-savings/risk calculations | 960 | 288
21 | D8. Medicaid Enterprise Data Warehouse (EDW) Connector | Data Connector | 3 | Backend — feeds Program Analytics Dashboard (P6) | State Medicaid EDW batch extracts | Cross-MCO longitudinal claims/eligibility resources into C1/C2 | 640 | 224
22 | D9. All-Payer Claims Database (APCD) Connector | Data Connector | 3 | Backend — feeds Program Analytics Dashboard (P6) | State APCD batch extracts (Medicaid, Medicare, commercial claims) | Cross-payer longitudinal claims resources into C1/C2 | 640 | 224
23 | D10. Public Health Connector (Immunization IIS + Vital Records) | Data Connector | 3 | Backend — status shown in Admin Console | State/local IIS query responses; vital records batch feed | Immunization and vital-status resources into C1/C2 | 480 | 168
| TOTAL — ALL MODULES | [5 empty] | 15280 | 5880